## Sheet1
PROJECT X: AUTOMATED ATTENDANCE SYSTEM
Start Date: Mar 3 | End Date: May 2 | Actual Start Date: Mar 3 | Actual End Date:
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Estimated Duration (Day) | Assignee | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status | Actual Duration (Day)
T1 | Requirements Gathering | ST1.1 | Identify initial system requirements | Initial Requirements Document | 1 | Barbas | 2025-03-03 | 2025-03-03 | 2025-03-03 | 2025-03-03 | Completed | 1
|  | ST1.2 | Refine requirements | Updated Requirements Document | 1 | Verdeflor | 2025-05-03 | 2025-06-03 | 2025-05-03 | 2025-07-03 | Completed | 1
|  | ST1.3 | Conduct elicitation | Stakeholder Feedback Report | 1 | Barbas | 2025-07-03 | 2025-08-03 | 2025-08-03 | 2025-09-03 | Completed | 1
|  | ST1.4 | Refine requirements after elicitation | Finalized Requirements Document | 1 | Barbas | 2025-08-03 | 2025-09-03 | 2025-09-03 | 2025-10-03 | Completed | 1
T2 | System Analysis & Design | ST2.1 | Develop Use Case Scenarios | Use Case Diagrams & Descriptions | 2 | Velasco | 03/17/2025 | 03/19/2025 | 03/17/2025 |  | In Progress
|  | ST2.2 | Create Conceptual Diagram | Conceptual Model Diagram | 2 | Velasco | 03/17/2025 | 03/19/2025 | 03/17/2025 |  | In Progress
|  | ST2.3 | Develop Traceability Matrix | Requirements Traceability Matrix | 2 | Barbas | 03/17/2025 | 03/19/2025 | 03/17/2025 |  | In Progress
T3 | System Design | ST3.1 | Design Database Schema | ER Diagram, MySQL Schema | 3 | Verdeflor | 03/27/2025 | 02/29/2025 |  |  | Pending
|  | ST3.2 | Design System Architecture | System Architecture Document | 2 | Verdeflor | 03/29/2025 | 03/31/2025 |  |  | Pending
T4 | Development Phase | ST4.1 | Develop REST API Backend | API with CRUD Operations | 3 | Verdeflor | 2025-01-04 | 2025-04-04 |  |  | Pending
|  | ST4.2 | Develop Frontend UI | Mobile Interface | 4 | Velasco | 2025-04-04 | 2025-08-04 |  |  | Pending
|  | ST4.3 | Implement Device Registration Module | Authentication & Device Management | 4 | Barbas | 2025-08-04 | 2025-12-04 |  |  | Pending
|  | ST4.4 | Implement Attendance Tracking Module | Attendance Logging System | 4 | Verdeflor | 2025-12-04 | 04/16/2025 |  |  | Pending
T5 | Testing & Quality Assurance | ST5.1 | Unit Testing | Unit Test Reports | 2 | Barbas | 04/18/2025 | 04/21/2025 |  |  | Pending
|  | ST5.2 | System Testing | System Test Reports | 2 | Barbas | 04/21/2025 | 04/23/2025 |  |  | Pending
T6 | Deployment & Training | ST6.1 | Deploy System | Deployment | 2 | Verdeflor | 04/25/2025 | 04/27/2025 |  |  | Pending
T7 | Project Closure | ST7.1 | Final Review & Sign-off | Closure Report & Handover Documentation | 1 | Velasco | 2025-01-05 | 2025-02-05 |  |  | Pending